## Calcs
Fill in the cells in green below per the Notes field. Most green fields are numbers in weeks with exception of the 'Other Items' cells which are percentages. If you have any questions or want to work with our team to get an accurate estimate, please contact us at hello@adattivo.co.
Adattivo Software Development Project Cost Calculator
| Estimate (weeks) | Notes
Design
Web Design | 0 | 3-4 weeks depending on how many screens and depending on how complicated the flow is.
Mobile Design | 0 | 3-4 weeks depending on how many screens and depending on how complicated the flow is.
Clickable Demo | 0 | 2-3 weeks per mobile or web, depending on complications above
Total Design | 0
Web Application
Base Project | 0 | 1 week to setup project and build skeleton code and repo process.
Identity/Security | 0 | 2-3 weeks depending on 3rd party authentication and number of extras like multifactor authentication
Payments | 0 | 1-2 weeks to integrate to 3rd party processor like Stripe or Paypal Braintree
Reporting | 0 | 1-2 weeks for basic reporting and 3-4 weeks for more complicated
Notifications | 0 | 1 week for notification settings and 1 week for browser notifications
3rd Party Integrations | 0 | 1-2 weeks per 3rd party integraions
Secret Sauce | 0 | 5-10 depending on how complex your idea is and how many different screens will need to be built
Mobile Application
Base Project | 0 | 1 week to setup project and build skeleton code and repo process.
Identity/Security | 0 | 1-2 weeks depending on 3rd party authentication and number of extras like multifactor authentication
Payments | 0 | 1-2 weeks to integrate to 3rd party processor like Stripe or Paypal Braintree
Reporting | 0 | 1-2 weeks for basic reporting and 3-4 weeks for more complicated
Notifications | 0 | 1-2 weeks for mobile notifications
3rd Party Integrations | 0 | 1-2 weeks per 3rd party integraions
Secret Sauce | 0 | 5-10 depending on how complex your idea is and how many different screens will need to be built
Mobile Application
Base Project | 0 | 1 week to setup project and build skeleton code and repo process.
Identity/Security | 0 | 2-3 weeks depending on 3rd party authentication and number of extras like multifactor authentication
Payments | 0 | 1-2 weeks to integrate to 3rd party processor like Stripe or Paypal Braintree
Reporting | 0 | 1 week for reporting
Notifications | 0 | 1 week for basic email and 1 week for SMS
3rd Party Integrations | 0 | 1-2 weeks per 3rd party integraions
Secret Sauce | 0 | 8-12 depending on how complex your idea is and how many different screens will need to be built
Total Development (weeks) | 0
Other Items
Project Mgmt | 0.1 | 10-15% of overall cost depending on how much oversite you want on the project
Testing | 0.25 | 25-40% of overall costs depending on how deep you want to test
Internationalization | 0 | 5% of dev cost for each locale
Feature Appetite | 0.1 | Can add up to 33% of overall cost. This ranges from 0 if you want a basic/bare bones MVP release to get immediate feedback from the user and 33% if you want everything pixel perfect and the kitchen sink included in first release. 10-15% is a good mix between the two.
Totals
Design | 0
Development | 0
PM | 0
Testing | 0
Intl | 0
Estimate (weeks) | 0
Estimate after Feature Appetite | 0 | This is the total number of resource weeks. We can put multiple dev, PM, and test resources on the project to hit a specific calendar date.
Hourly Rate | 145 | Adattivo's base rate
Weekly Rate | 5220 | We average 36 hours a week
Overal Costs | 0 | This estimate is meant to be a ballpark estimate depending on your answers above. To get a more accurate estimate, please reach out to our team at hello@adattivo.co and let us go through estimation process with you.
For more info or if you have any questions, contact us at hello@adattivo.co or 720-744-2396

## Example
This example is estimate of a web application with API that already had designs and with an average complication factor. We don't want bare bones, but don't quite need the kitchen sink. It also included us doing simple testing and basic project management.
Adattivo Software Development Project Cost Calculator
| Estimate (weeks) | Notes
Design
Web Design | 0 | 3-4 weeks depending on how many screens and depending on how complicated the flow is.
Mobile Design | 0 | 3-4 weeks depending on how many screens and depending on how complicated the flow is.
Clickable Demo | 0 | 2-3 weeks per mobile or web, depending on complications above
Total Design | 0
Web Application
Base Project | 1 | 1 week to setup project and build skeleton code and repo process.
Identity/Security | 2 | 2-3 weeks depending on 3rd party authentication and number of extras like multifactor authentication
Payments | 1 | 1-2 weeks to integrate to 3rd party processor like Stripe or Paypal Braintree
Reporting | 1 | 1-2 weeks for basic reporting and 3-4 weeks for more complicated
Notifications | 1 | 1 week for notification settings and 1 week for browser notifications
3rd Party Integrations | 2 | 1-2 weeks per 3rd party integraions
Secret Sauce | 8 | 5-10 depending on how complex your idea is and how many different screens will need to be built
Mobile Application
Base Project | 0 | 1 week to setup project and build skeleton code and repo process.
Identity/Security | 0 | 1-2 weeks depending on 3rd party authentication and number of extras like multifactor authentication
Payments | 0 | 1-2 weeks to integrate to 3rd party processor like Stripe or Paypal Braintree
Reporting | 0 | 1-2 weeks for basic reporting and 3-4 weeks for more complicated
Notifications | 0 | 1-2 weeks for mobile notifications
3rd Party Integrations | 0 | 1-2 weeks per 3rd party integraions
Secret Sauce | 0 | 5-10 depending on how complex your idea is and how many different screens will need to be built
Mobile Application
Base Project | 1 | 1 week to setup project and build skeleton code and repo process.
Identity/Security | 2 | 2-3 weeks depending on 3rd party authentication and number of extras like multifactor authentication
Payments | 1 | 1-2 weeks to integrate to 3rd party processor like Stripe or Paypal Braintree
Reporting | 1 | 1 week for reporting
Notifications | 1 | 1 week for basic email and 1 week for SMS
3rd Party Integrations | 2 | 1-2 weeks per 3rd party integraions
Secret Sauce | 10 | 8-12 depending on how complex your idea is and how many different screens will need to be built
Total Development Weeks | 34
Other Items
Project Mgmt | 0.1 | 10-15% of overall cost depending on how much oversite you want on the project
Testing | 0.25 | 25-40% of overall costs depending on how deep you want to test
Internationalization | 0 | 5% of dev cost for each locale
Feature Appetite | 0.1 | Can add up to 33% of overall cost. This ranges from 0 if you want a basic MVP release to get immediate feedback from the user and 33% more if you want everything pixel perfect and the kitchen sink included in first release.
Totals
Design | 0
Development | 34
PM | 3.4
Testing | 8.5
Intl | 0
Estimate in weeks | 45.9
Estimate after Feature Appetite | 50.49
Hourly Rate | 145 | Adattivo's base rate
Weekly Rate | 5220 | We average 36 hours a week
Overal Costs | 263557.8
For more info or if you have any questions, contact us at hello@adattivo.co or 720-744-2396